## Features
Role | Responsibility | Status | Remarks | Task effort | Effort in hours
RMG Admin | Create employee | Completed
| Manage Bench | Completed | add resource to project
| Generate reports | YTD
| Generate and update Project code | Completed | Currently code is created outside and added here. Generation of code is not done here
Project Manager (PM) | Add resource to Project | Completed
| Create task for Project | YTD
| Approve/Reject timesheet | Completed
| View/edit timesheet of resources | Completed | edit timesheet feature yet to be implemented | Medium
| Authenticate timesheet | YTD
| Project closure initiation | YTD
Delivery Head (DH) | Approve project creation/closure | Completed
Assign PM for project
Sales Team | Project initiation / creation | Completed
Employee | View and edit timesheet | WIP | edit timesheet feature yet to be implemented | Medium | High priority
Finance Team | Generate invoice for projects | YTD

## MOM
Sno | Requested By | Description | Module/Section | MOM Date | Owner | Status | Remarks
1 | Ashok kumar | Minimu character requirements in Employee ID>5 | Add Employee Section | 2021-08-10 | Frontend
2 | Ashok kumar | Manger ID should be validated in the Backend to check if such a Manager ID exist | Add Employee Section | 2021-08-10 | Backend
3 | Ashok kumar | when typing the manager ID, it should show the manager name by searching from the backend to double verify the manager Name | Add Employee Section | 2021-08-10 | Frontend
4 | Ashok kumar | Salutation should be Mr, Miss, Mrs, M/S from the dropdown instead of free text | Add Employee Section | 2021-08-10 | Frontend
5 | Ashok kumar | Project code should be a required field only if the "resource status is changed to Billable" else it should be a optional field | Add Employee Section | 2021-08-10 | Frontend
6 | Ashok kumar | Project code should be a drop downfield from the unique list of projects from the projects table-new API needed | Add Employee Section | 2021-08-10 | Both
7 | Ashok kumar | Department should be a drop down, this will be populated from the Department table | Add Employee Section | 2021-08-10 | Frontend
8 | Ashok kumar | Create new table called department and API to add data to the department, | Add Employee Section | 2021-08-10 | Frontend
9 | Ashok kumar | Create a page which is used to add department, this should be visible to the RMG admin | Add Employee Section | 2021-08-10 | Frontend
10 | Ashok kumar | Designation should be a dropdown, this will be populated from the Designation table, | Add Employee Section | 2021-08-10 | Frontend
11 | Ashok kumar | Create a new table called designation and API tp add and view data to the designation | Add Employee Section | 2021-08-10 | Frontend
12 | Ashok kumar | createa page which is used to add designation, this should be visible to the RMG admin | Add Employee Section | 2021-08-10 | Frontend
13 | Ashok kumar | resource status should be Drop down-Billable, Non Billable. This should be hard code and available from frontend itself | Add Employee Section | 2021-08-10 | Frontend
14 | Ashok kumar | delivery type should be dropdown-Keep two values just for now. Will give the actual values later. This should be hard coded and availabe from the frontend itself | Add Employee Section | 2021-08-10 | Frontend
15 | Ashok kumar | roles should be multi select combo box, this should be sent as a string cancatenated with comma. Values should be RMG admin, Employee, Project Manager, Sales Team, Finance Team | Add Employee Section | 2021-08-10 | Frontend
16 | Ashok kumar | Filter to be added for Salutation, Project Name, Resource Status, Manager Name, Delivery type | View Employee Section | 2021-08-10 | Frontend
17 | Ashok kumar | Sorting should be added for Full Name, Project Assigned Date, Project End Date, Skills | View Employee Section | 2021-08-10 | Frontend
18 | Ashok kumar | From Date and To Date filter need to be added -UI complete, Functionality missing | Time Submissions | 2021-08-10 | Frontend
19 | Ashok kumar | For modal showing approved time submissions for users-move the download section to the top next to the Submission and time type | Time Submissions | 2021-08-10 | Frontend
20 | Ashok kumar | For modal showing approved time submissions for users-Add Scroll and Keep the Header Freezed | Time Submissions | 2021-08-10 | Frontend
21 | Ashok kumar | For modal showing approved time submissions for total, Remove the Submission, Keep only the Time type. | Time Submissions | 2021-08-10 | Frontend
22 | Ashok kumar | For all modal while clicking on the numbers, Freeze the Header and make just the content scrollable, Move the Download section to the top | Time Submissions | 2021-08-10 | Frontend
23 | Ashok kumar | In the main page,Freeze the Filter and Header section and make the content scrollable | Time Submissions | 2021-08-10 | Frontend
24 | Ashok kumar | Add Validation for Client Name-Minimum Character-10 | Add Project | 2021-08-10 | Frontend
25 | Ashok kumar | Add Validation for Project Code-Minimum Character-10 | Add Project | 2021-08-10 | Frontend
26 | Ashok kumar | Add Validation for Project Name-Minimum Character-10 | Add Project | 2021-08-10 | Frontend
27 | Ashok kumar | Remove Project Status-It will be handled in the backend | Add Project | 2021-08-10 | Frontend
28 | Ashok kumar | Billing Type should be Drop Down-Ask Nataraj/Ashok for the types | Add Project | 2021-08-10 | Frontend
29 | Ashok kumar | Segment, Geography should be dropdown-Ask Nataraj/Ashok for the types | Add Project | 2021-08-10 | Frontend
30 | Ashok kumar | Solution Category should be Drop down-Ask Natarj/Ashok for the types | Add Project | 2021-08-10 | Frontend
31 | Ashok kumar | Financial Year should be drop down-like 2021-2022, etc | Add Project | 2021-08-10 | Frontend
32 | Ashok kumar | Add Sorting to Billing type, Segment, Geography, Solution Category, Financial Year, Project Code | View Project | 2021-08-10 | Frontend
33 | Ashok kumar | Default value for Hours should be 8 | Time Summary-Modal | 2021-08-10 | Frontend
34 | Ashok kumar | Shorten the size of Description and remarks to match Task ID | Time Summary-Modal | 2021-08-10 | Frontend
35 | Ashok kumar | Task ID should be smaller field Like Project ID | Time Summary-Modal | 2021-08-10 | Frontend
36 | Ashok kumar | Align the Lable and Field inputs for better aesthetics | Time Summary-Modal | 2021-08-10 | Frontend
37 | Ashok kumar | Bug Fix-Once the user logged in, it doesn’t show the Left Nav. User need to refresh the page to see the left nav | Left Nav | 2021-08-10 | Frontend
38 | Ashok kumar | Bug Fix-once the user logged out, the space occupied by the left nav is still visible, User need to refresh the page to make it go away | Left Nav | 2021-08-10 | Frontend
39 | Ashok kumar | While loggin in , pressing enter does not login, instead the user has to press submit | Login page | 2021-08-10 | Frontend
40 | Ashok kumar | Add token in the header in all calls to backend API | All pages | 2021-08-10 | Frontend
41 | Ashok kumar | Add role based filter-content should be shown only to the respective roles givne in the feature tab | All pages | 2021-08-10 | Frontend
42 | Ashok kumar | Add auth to all endpoints in the backend | All endpoints | 2021-08-10 | Backend
43 | Ashok kumar | Add token expiry info in the auth token in the backend | Auth module | 2021-08-10 | Backend